## Sheet1
Deliverables | Delivery Date
Design Document | 8/7 - 08/09
Phase I
Implementation of book and customer registration | 08/10 - 08/17
online book order, rental reservation
staff and customer book searches
staff edit book information
use In Memory H2 Database and replace it to MySql in Phase II
Phase II
Implement the rest of the functionality like generating reports | 08/18 - 08/31
Migrate from H2 DB to Mysql
implment MVC architecture with Spring Rest
Add authentication of staff and users, used encryped passwords
Phase III
Implement requirment changes
Add a UI Component using AngularJS 2
Deploy in tomcat and test the functionality
Phase IV
Use CICD with Jenkins
Implement Aouth 2 for authentication and authorization